CITY REGION DEAL JOINT COMMITTEE
ROLLING ACTIONS LOG

CITY REGION DEAL JOINT COMMITTEE
ROLLING ACTIONS LOG

| Date | Report title | Action | Action owner | Completion date (expected) | Comments |
| --- | --- | --- | --- | --- | --- |
| 9th March 2021 | Outcomes of the Delegated Group Work on Implementation Plan | To approve the proposal to bring forward a paper to November Joint Committee on an Innovation Thematic Board to support the work of the Innovation Investment Strand | John Rogers | End of 2022 | It was previously agreed that this action would be taken forward after SCREAB and REF had been established. Now that those have been overtaken by the REAG, which can provide advice on a wide range of economic matters including innovation, the need for a separate Innovation Thematic Board has been removed. It is recommended that this action be closed. |
| 21st July 2021 | MOD Forthside | Verbal update regarding current status of the Business case and progression through Government process to allow for Land Transfer | Brian Roberts | Autumn 2023 | The SOC for the MOD land at Forthside is a substantive action on the agenda for the October meeting of Joint Committee. It is recommended that this action be closed. |
| 7th September 2021 | Update on the Business Case Development Process | To receive regular feedback on issues in the business case journey in order that the appropriate action and intervention may occur. | RPMO | Ongoing | Regular updates on this issue are presented by the relevant SRO as each business case is progressing, so it is recommended that this action be closed as a stand alone item. |
| 22nd June 2023 | Programme Status Report | Recruitment of New Head of RPMO | BR | Complete | Recruitment completed and successful candidate starts on 16th October 2023. It is, accordingly, recommended that this item be closed. |